## Remaining Priorities
Rank | Task | Description | Area | Priority | Estimated Effort (days) | ETA (date) | Status | Next Action | Owner
1 | Verify exemplars in backend | Validate exemplar emission and trace correlation by configuring METRICS_OTLP_URL to a collector and verifying exemplars. | Telemetry/OTEL | High | 2 | Pending | Provide OTLP collector endpoint and run CI | Dev/Infra | 2026-01-20
2 | Full OTLP protobuf exporter path | Implement non-SDK OTLP protobuf encoding or ensure SDK path reliably used in CI. | Telemetry/OTLP | High | 5 | In Progress | Decide SDK vs direct encoder; implement chosen path | Dev | 2026-01-23
3 | Prometheus metrics labels and exemplars | Ensure metrics include trace_id labels when available and exemplars emitted for request-level metrics. | Telemetry/Prometheus | High | 3 | In Progress | Exercise with collector and adjust exporter | Dev | 2026-01-21
4 | Convert example workflow to reusable workflow | Refactor `.github/workflows/prometheus-scrape-example.yml` into a reusable workflow callable by other repos. | CI | Medium | 2 | Pending | Create reusable workflow and update docs | Dev/Ops | 2026-01-20
5 | Tighten CI assertions | Add stricter assertions for labeled metrics and trace_id presence in CI tests. | CI/Tests | High | 1 | Pending | Add checks and run CI with METRICS_OTLP_URL | QA/Dev | 2026-01-19
6 | OTEL SDK initialization hardening | Finalize `_start_opentelemetry_sdk` fallback logic and test across OTEL versions. | Telemetry/OTEL | Medium | 3 | In Progress | Add unit tests and smoke runs across versions | Dev | 2026-01-21
7 | Expose persisted metrics for long-term analysis | Ship JSONL artifacts to an artifacts store or S3 for historical analysis. | Observability | Medium | 2 | Pending | Add CI upload + retention policy | Ops | 2026-01-20
8 | TokenTracker integration coverage | Extend TokenTracker integration across all agent tool calls and add per-tool budgets and alerts. | Agent/TokenTracker | High | 4 | Partially Done | Audit agent wrappers and add missing hooks | Dev | 2026-01-22
9 | Performance benchmarks for cache | Run larger scale benchmarks and report latency/throughput tradeoffs for different cache sizes and TTLs. | Caching/Perf | Medium | 3 | Pending | Run `tools/cache_benchmark.py` with datasets and collect results | Perf | 2026-01-21
10 | Add production OTLP config docs | Document required env vars (`METRICS_OTLP_URL`, headers, timeouts) and secure secret handling. | Docs/Onboarding | Medium | 1 | Pending | Draft README and examples | Docs | 2026-01-19
11 | Reusable exemplar validation harness | Create a small harness that sends synthetic token records and validates exemplars appear in backend. | Telemetry/Test | Low | 2 | Pending | Implement harness and CI job | QA | 2026-01-20
12 | Alerting for token budget breaches | Add alerts when TokenTracker reports budget exceed or anomalous token growth. | Ops/Monitoring | Medium | 3 | Pending | Wire metrics to alerting rules | Ops | 2026-01-21
Generated: 2026-01-18T08:52:06.270596Z