## Week5 Priorities
Rank | Task | Description | Area | Priority | Estimated Effort (days) | ETA (date) | Status | Next Action | Owner
1 | Multi-agent orchestration | Finalize orchestrator and agent interaction flows. | Orchestration | High | 5 | Pending | Integrate orchestrator into research-assistant | Dev | 2026-01-23
2 | Memory system: knowledge graph | Implement knowledge-graph based memory and APIs. | Memory | High | 6 | Pending | Prototype memory.graph and connectors | Dev | 2026-01-24
3 | Production OTLP config + secrets | Document and template production OTLP exporter configs and secret handling. | Ops | High | 2 | Pending | Draft README and example env files | Ops | 2026-01-20
4 | Finalize exemplars backend verification | Complete CI collector verification and document results. | Telemetry | High | 2 | In Progress | Run CI with METRICS_COLLECTOR_URL | Dev/Infra | 2026-01-20
5 | TokenTracker per-tool budgets | Add per-tool budget alerts and dashboards. | Observability | Medium | 3 | Pending | Add alert rules and dashboards | Ops/Dev | 2026-01-21
6 | Cache performance scale tests | Run large-scale cache benchmarks and produce report. | Caching | Medium | 4 | Pending | Run `tools/cache_benchmark.py` | Perf | 2026-01-22
Generated: 2026-01-18T13:19:27.272073Z